## README
Tinku Math — Master Task Tracker
CBSE primary-math kids' app · built solo from Dubai, targeting India
HOW THIS WORKBOOK IS ORGANISED
Tab | What it contains
All Tasks | Every task (1-70) we discussed, grouped by workstream, with priority, dependencies and status. Your master list.
Build Order (MVP→) | The SAME tasks re-sequenced the way they should actually be built: MVP first, then Phase 2, 3, 4. Use this to decide what to do next.
MVP Definition | The precise cut line — what MUST be in the first public launch vs. what waits. Read this before building anything.
Roadmap Gates | The quarter-by-quarter decision gates from Plan A, summarised.
HOW TO USE IT
1 | Work top-to-bottom in the 'Build Order' tab — it is already dependency-sorted.
2 | Update the Status column as you go (Not started / In progress / Done / Blocked).
3 | Anything marked MVP must ship for launch. Phase 2+ can wait — do not let it delay launch.
4 | The single most important non-code task is kid-testing (T66). Do not skip it.
PRIORITY LEGEND
High | Critical path — blocks launch or other work
Medium | Important but not launch-blocking
Quick win | Small effort, do whenever
Later | Post-launch / future version
THE ONE RULE
Until Month 6, measure success by RETENTION and REVIEWS, not revenue. D7 retention is the number that decides everything.

## All Tasks
All Tasks — Master List (grouped by workstream)
ID | Task | Details | Workstream | Priority | Phase | Depends on | Status
T61 | Skill map w/ prerequisites (G1-G2) | ~30 atomic skills per grade as a prerequisite graph; replaces flat syllabus list. 2 evenings w/ NCERT. | Learning Engine | High | MVP | - | Not started
T2 | Question generator core + templates | Template = param ranges + answer + misconception-tagged distractors. 5 templates for MVP (counting, add within 10/20, subtract, place value). | Learning Engine | High | MVP | T61 | Not started
T62 | Misconception research per topic | Common error list per skill (NCERT teacher handbooks) to drive distractors + hints. 1 evening/grade. | Learning Engine | Medium | MVP | T61 | Not started
T65 | Indian context bank | Names, items (laddoos, mangoes), ₹ denominations, scenes for word problems & visuals. One file. | Learning Engine | Quick win | MVP | - | Not started
T6 | Adaptive difficulty | Within-session: 2 correct -> harder (max 3); remediation handles downshift. Carry difficulty between sessions. | Learning Engine | High | MVP | T2 | Not started
T46 | Remediation ladder (wrong-answer flow) | Wrong1=hint, Wrong2=visual walkthrough+retry easier, Wrong3=park skill+guaranteed-win question (mood floor). Never punish. | Learning Engine | High | MVP | T2 | Not started
T63 | Spaced repetition (Leitner 5-level) | 'Tinku's Memory Boxes' — mastered skills resurface at 1/2/4/7/21 day intervals. Powers retention proof. | Learning Engine | High | MVP | T2 | Not started
T64 | Session composer + mood floor | ~10 Q/session: 1 warm-up win + 5 frontier + 4 review. Free daily dose is pedagogically complete by design. | Learning Engine | High | MVP | T63 | Not started
T8 | Tests for QuizEngine | Vitest + RTL on scoring, validation, question selection — the component where bugs give kids wrong feedback. | Learning Engine | Medium | MVP | T2 | Not started
T67 | TTS instruction audio (en-IN) | Pre-generated voice for instructions; unlocks word-problem format for non-reading G1 kids. Hindi later. | Learning Engine | Medium | Phase 2 | T2 | Not started
T53 | Anonymous auth from first launch | signInAnonymously() on first open; every guest is a real UID. Foundation for all progress. | Auth & Accounts | High | MVP | - | Not started
T54 | Guest progress persistence check | Verify refresh/reinstall doesn't wipe data; Firestore writes keyed to anon UID + offline persistence. | Auth & Accounts | High | MVP | T53 | Not started
T3 | Child profiles + progress persistence | Parent account holds multiple child profiles (siblings); progress docs under auth UID. | Auth & Accounts | High | MVP | T54 | Not started
T55 | Account linking (phase switchover) | linkWithCredential/Popup — anon UID upgrades to Google account, ZERO progress loss. Never lose streak/pet. | Auth & Accounts | High | MVP | T53 | Not started
T56 | Login trigger moments | Sign-in prompted only at value moments (save streak, dashboard, purchase, sibling, device switch). Never at open. | Auth & Accounts | High | MVP | T55 | Not started
T57 | Parent-framed login screen | 'Parents: sign in to save progress & view reports' — frames account creation as parent action (DPDP). | Auth & Accounts | High | MVP | T56 | Not started
T58 | Sign-in required at purchase | Map subscription to a Firebase UID so premium restores on new devices. | Auth & Accounts | Medium | MVP | T55 | Not started
T59 | Auth edge cases | Google account already linked elsewhere, cancelled link mid-flow, multi-device anon conflicts. | Auth & Accounts | Medium | Phase 2 | T55 | Not started
T60 | Auth state in analytics | Tag events anon vs linked; measure conversion of the streak-save prompt itself. | Auth & Accounts | Later | Phase 2 | T47 | Not started
T31 | Daily practice limit mechanic | Free=1-2 sessions/day; limit lands softly at session end (never mid-quiz). 'Ask your parent' -> kid becomes sales agent. | Monetization | High | MVP | T64 | Not started
T35 | Final free/premium tier matrix | Free: lessons,1-2 sessions,basic streak+pet,current chapter,weekly summary. Paid: unlimited,detailed reports,themes,offline,all siblings. | Monetization | High | MVP | T31 | Not started
T32 | Dashboard teaser (gated insight) | Free shows summary + 'one area needs attention - unlock'; full weak-area analytics behind paywall. | Monetization | High | MVP | T4 | Not started
T33 | Paywall screen + copy | Anchor to tuition: 'less than one tuition class/month'; sibling math. Never compare to free alternatives. | Monetization | High | MVP | T35 | Not started
T34 | Mastery-proof upgrade triggers | Upgrade prompts fire only AFTER delivered results (~2 weeks), never day one. | Monetization | High | MVP | T63 | Not started
T39 | Soft-limit UX rules | No paywalls interrupting a child mid-activity; all monetization screens parent-directed (Families Policy). | Monetization | High | MVP | T31 | Not started
T13 | Set up Play Billing subscriptions | ₹ price points set manually (₹99-149/mo, ₹999/yr); Google handles UPI + GST for foreign devs. | Monetization | High | MVP | T58 | Not started
T36 | Kid-side premium perks | Pet accessories, exclusive avatars/themes as subscription benefits — gives the child a reason to lobby. | Monetization | Medium | Phase 2 | T35 | Not started
T37 | Weekly parent progress summary | One-line free summary (push/WhatsApp/email): 'practiced 4 days this week' — feeds conversion moments. | Monetization | Medium | Phase 2 | T4 | Not started
T38 | Exam-season upgrade triggers | 'Unit test coming? Unlock Chapter 4-6 pack' — timed prompts around school calendar. | Monetization | Medium | Phase 2 | T35 | Not started
T40 | Sibling/family plan logic | One subscription covers all child profiles; surface on paywall + dashboard. | Monetization | Medium | Phase 2 | T35 | Not started
T22 | Exam-season crash packs | Short-term ₹199-499 packs timed to assessments. | Monetization | Later | Phase 3 | T38 | Not started
T4 | Parent dashboard (paid hook) | Topic mastery, streaks, weak areas per child. Split: free summary layer vs premium detail layer. THE thing parents pay for. | Parent Dashboard | High | MVP | T3 | Not started
T41a | Mascot v0 (Tinku) — 3-6 poses | Elephant + math star. happy/celebrate/encourage done; thinking/sleeping/waving remaining. Gemini-generated. | Mascot & Brand | High | MVP | - | Not started
T42 | Character-driven feedback layer | Static mascot images on result screens at launch (full animated layer post-launch). | Mascot & Brand | Medium | MVP | T41a | Not started
T52 | Tinku name check (Play Store + IP) | 5-min search for existing 'Tinku' kids/education apps before printing on the store. | Mascot & Brand | Quick win | MVP | - | Not started
T44 | Daily quests + streak system | 3-5 min sessions, daily quest, streak counter owned by Tinku. | Mascot & Brand | High | MVP | T64 | Not started
T9 | Repo hygiene | Fix 'CBSC'->'CBSE', add LICENSE, make repo private (commercial). | Mascot & Brand | Quick win | MVP | - | Not started
T45 | Parent-directed streak notifications | Playful reminders to PARENT's device only; no guilt-tripping the child (Families Policy). | Mascot & Brand | Medium | Phase 2 | T44 | Not started
T48 | Hinglish character voice/copy | 'Shabash!', 'koi baat nahi' — Tinku dialogue localization layer. | Mascot & Brand | Medium | Phase 2 | T41a | Not started
T43 | Sound design pack | Correct ding, celebration, streak sounds — dopamine layer (stock sounds fine for MVP). | Mascot & Brand | Later | Phase 2 | - | Not started
T49 | Mascot WhatsApp stickers/share cards | Tinku-branded achievement cards + sticker pack for organic spread. | Mascot & Brand | Later | Phase 2 | T41a | Not started
T41b | Mascot full expression set (6-8) | Complete polished expression set beyond the v0 minimum. | Mascot & Brand | Later | Phase 2 | T41a | Not started
T50 | Supporting cast (v2) | Dadi-encourager, rival kid, teacher-guide; cuter for Wonder, cooler for Explorer. | Mascot & Brand | Later | Phase 3 | T41a | Not started
T5 | Theme token architecture | Tailwind CSS vars; theme-wonder (G1-3) now; structure ready for theme-explorer (4-5) later. | Theming & Bands | Medium | MVP | - | Not started
T24 | Explorer band (Grades 4-5) | Space/detective skins, leaderboards, XP — same engine, new tokens; 'graduation' event from Wonder. | Theming & Bands | Later | Phase 2 | T5 | Not started
T25 | Child-selectable skins per band | 2-3 themes per band (kid picks, no gendered themes); premium themes as upsell. | Theming & Bands | Later | Phase 2 | T24 | Not started
T1 | Ship skill map + templates as code, state in Firestore | REVISED: with a generator there are no question banks to host. Templates=code; only child state in Firestore. | Content Architecture | High | MVP | T2 | Not started
T10 | Google Play Console - individual account | $25 one-time, UAE identity, link UAE bank for payouts. | Packaging & Launch | High | MVP | - | Not started
T11 | Families Policy compliance | Privacy policy, no ads targeting kids, parent-creates-account (DPDP consent). Start EARLY — longest external wait. | Packaging & Launch | High | MVP | T57 | Not started
T12 | Wrap PWA for Play Store | Capacitor (or TWA) — same codebase ships Android now, iOS later. | Packaging & Launch | High | MVP | - | Not started
T14 | Define free vs premium tiers | (Superseded by T35 final matrix.) | Packaging & Launch | High | MVP | T35 | Not started
T15 | Verify Play tax settings for India | Confirm Google remits GST as merchant in Console tax config. | Packaging & Launch | Medium | MVP | T10 | Not started
T16 | Cross-border CA consultation | One session on UAE<->India tax (DTAA, where profits taxed) before first revenue. | Packaging & Launch | Medium | MVP | - | Not started
T27 | iOS launch | ~Month 6 or when Android revenue covers it; Capacitor makes it cheap. | Packaging & Launch | Later | Phase 3 | T12 | Not started
T17 | ASO listing | Keywords: 'CBSE maths class 1','NCERT','class 2 maths practice'; strong screenshots. | Go-to-Market | High | MVP | T41a | Not started
T18 | Seed 50-100 parents | Free premium via mom FB/WhatsApp groups for feedback + reviews. | Go-to-Market | High | Launch | T17 | Not started
T19 | WhatsApp share cards | Achievement certificates/streak badges parents forward — built-in virality. | Go-to-Market | Medium | Phase 2 | T49 | Not started
T20 | Mom micro-influencers | 10K-100K follower parenting accounts, ₹2-15K/post. | Go-to-Market | Medium | Phase 2 | T17 | Not started
T21 | Teacher/school outreach | Free classroom access to 10-20 local G1-2 teachers; cheapest distribution long-term. | Go-to-Market | Medium | Phase 2 | - | Not started
T23 | Paid ads test (Google UAC) | ₹10-15K/month — ONLY after organic conversion proven. | Go-to-Market | Later | Phase 3 | T23 | Not started
T29 | B2B school sales | ₹50-100/student/year to budget private schools; may need Indian entity. Fastest path to real rupees. | Go-to-Market | Later | Phase 3 | T21 | Not started
T28 | State board content (2-3 big boards) | Maharashtra/UP first, vernacular-led — higher ROI than a second subject (engine already does math). | Go-to-Market | Later | Phase 4 | T61 | Not started
T30 | Direct web billing (Razorpay) | Only after ~₹3-5L/month — triggers OIDAR GST registration + monthly GSTR-5A. | Go-to-Market | Later | Phase 4 | T13 | Not started
T47 | Firebase Analytics instrumentation | Funnel from day one: install->first lesson->D1/D7 retention->limit-hit->paywall view->subscribe. | Analytics | High | MVP | - | Not started
T51 | A/B testing setup | Firebase Remote Config to test paywall copy, limit thresholds, notification timing. | Analytics | Later | Phase 3 | T47 | Not started
T68 | Claude Project setup | Upload specs/tracker/character sheet; 200K context so every chat knows the project. | Tooling | High | MVP | - | Not started
T69 | Claude Code + Antigravity setup | Install Claude Code; CLAUDE.md conventions file shared with Antigravity for the cheap/boilerplate code. | Tooling | High | MVP | - | Not started
T70 | Decisions log file | One markdown line per decision; both AIs read it to avoid contradictory advice. | Tooling | Quick win | MVP | - | Not started
T66 | Kid testing round #1 (3 kids x 20 min) | Watch real 6-year-olds use it. Highest-leverage free action. Repeats monthly. | Tooling | High | Launch | - | Not started

## Build Order (MVP→)
Build Order — what to do, in sequence
Dependency-sorted. Work top to bottom. Finish each block before the next.
Step | ID | Task | Priority | Status
BLOCK 0 — Setup (this week, ~1 day total)
1 | T68 | Claude Project setup (upload specs) | High | Not started
2 | T69 | Claude Code + Antigravity + CLAUDE.md | High | Not started
3 | T70 | Decisions log file | Quick win | Not started
4 | T9 | Repo hygiene (CBSC->CBSE, LICENSE, private) | Quick win | Not started
5 | T52 | Tinku name check (Play Store + IP) | Quick win | Not started
BLOCK 1 — Learning loop core (≈2 weeks) — THE HEART
6 | T61 | Skill map w/ prerequisites (G1-G2) | High | Not started
7 | T65 | Indian context bank | Quick win | Not started
8 | T62 | Misconception research per topic | Medium | Not started
9 | T2 | Question generator core + 5 templates | High | Not started
10 | T1 | Templates as code, state in Firestore | High | Not started
11 | T46 | Remediation ladder (wrong-answer flow) | High | Not started
12 | T6 | Adaptive difficulty | High | Not started
13 | T8 | Tests for QuizEngine | Medium | Not started
BLOCK 2 — Accounts & persistence (≈1 week)
14 | T53 | Anonymous auth from first launch | High | Not started
15 | T54 | Guest progress persistence check | High | Not started
16 | T3 | Child profiles + progress persistence | High | Not started
17 | T63 | Spaced repetition (Leitner 5-level) | High | Not started
18 | T64 | Session composer + mood floor | High | Not started
BLOCK 3 — Mascot & feel (parallel, mostly Gemini)
19 | T41a | Tinku v0 — finish 6 poses | High | Not started
20 | T42 | Character-driven feedback layer (static) | Medium | Not started
21 | T44 | Daily quests + streak system | High | Not started
22 | T5 | Theme token architecture (Wonder band) | Medium | Not started
BLOCK 4 — Money loop (≈1 week)
23 | T31 | Daily practice limit mechanic | High | Not started
24 | T35 | Final free/premium tier matrix | High | Not started
25 | T4 | Parent dashboard (free + premium layers) | High | Not started
26 | T32 | Dashboard teaser (gated insight) | High | Not started
27 | T34 | Mastery-proof upgrade triggers | High | Not started
28 | T33 | Paywall screen + copy | High | Not started
29 | T39 | Soft-limit UX rules | High | Not started
30 | T55 | Account linking (switchover) | High | Not started
31 | T56 | Login trigger moments | High | Not started
32 | T57 | Parent-framed login screen | High | Not started
33 | T58 | Sign-in required at purchase | Medium | Not started
BLOCK 5 — Packaging & store (≈1 week, start T11 EARLY)
34 | T10 | Google Play Console account (UAE) | High | Not started
35 | T11 | Families Policy compliance (START EARLY) | High | Not started
36 | T12 | Wrap PWA w/ Capacitor | High | Not started
37 | T47 | Firebase Analytics instrumentation | High | Not started
38 | T13 | Play Billing subscriptions (₹ pricing) | High | Not started
39 | T15 | Verify Play tax settings for India | Medium | Not started
40 | T16 | Cross-border CA consultation | Medium | Not started
41 | T17 | ASO listing (keywords + screenshots) | High | Not started
BLOCK 6 — Reality check & launch
42 | T66 | Kid testing round #1 (3 kids x 20 min) | High | Not started
43 | T18 | Seed 50-100 parents -> reviews | High | Not started
PHASE 2 — Extend (post-launch, retention-gated)
44 | T24 | Explorer band (Grades 4-5) | Later | Not started
45 | T25 | Child-selectable skins per band | Later | Not started
46 | T67 | TTS instruction audio (en-IN) | Medium | Not started
47 | T36 | Kid-side premium perks | Medium | Not started
48 | T37 | Weekly parent progress summary | Medium | Not started
49 | T38 | Exam-season upgrade triggers | Medium | Not started
50 | T40 | Sibling/family plan logic | Medium | Not started
51 | T45 | Parent-directed streak notifications | Medium | Not started
52 | T48 | Hinglish character voice/copy | Medium | Not started
53 | T43 | Sound design pack | Later | Not started
54 | T49 | Mascot WhatsApp stickers/share cards | Later | Not started
55 | T41b | Mascot full expression set | Later | Not started
56 | T19 | WhatsApp share cards | Medium | Not started
57 | T20 | Mom micro-influencers | Medium | Not started
58 | T21 | Teacher/school outreach | Medium | Not started
59 | T59 | Auth edge cases | Medium | Not started
60 | T60 | Auth state in analytics | Later | Not started
PHASE 3 — Widen & monetize harder
61 | T27 | iOS launch | Later | Not started
62 | T50 | Supporting cast (v2) | Later | Not started
63 | T51 | A/B testing setup | Later | Not started
64 | T22 | Exam-season crash packs | Later | Not started
65 | T23 | Paid ads test (Google UAC) | Later | Not started
66 | T29 | B2B school sales | Later | Not started
PHASE 4 — Scale the engine (Year 2+)
67 | T28 | State board content (2-3 boards) | Later | Not started
68 | T30 | Direct web billing (Razorpay) | Later | Not started

## MVP Definition
MVP Definition — the launch cut line
The smallest thing worth a child's time and a parent's trust. Build this, launch, then expand.
MVP PRINCIPLE
The MVP must do ONE thing excellently: a child in Grades 1-3 practices CBSE math, struggles safely, improves over days, and a parent can see it working. Everything that doesn't serve that loop is Phase 2+.
MUST be in MVP (launch-blocking)
• | Learning loop: skill map (G1-3), question generator with 5+ templates, misconception-tagged distractors
• | Remediation ladder — the wrong-answer flow with the mood floor (never end on failure)
• | Spaced repetition (Leitner) + session composer — the daily dose that makes kids return
• | Adaptive difficulty within sessions
• | Anonymous auth + progress persistence (survives refresh/reinstall)
• | Child profiles (sibling support) under one account
• | Account linking: anonymous -> Google with ZERO progress loss
• | Parent dashboard v1 (free summary + gated premium detail)
• | Daily limit mechanic + paywall + tier matrix + parent-framed login
• | Play Billing subscriptions in ₹ (Google handles UPI + GST)
• | Tinku mascot v0 (6 poses) wired into feedback screens
• | Streak + daily quests
• | Wonder-band theme (Grades 1-3) with token architecture ready for Explorer later
• | Firebase Analytics (must measure D7 retention from day one)
• | Capacitor wrap + Play Console + Families Policy approval + ASO listing
• | Kid testing round #1 BEFORE public launch
Explicitly NOT in MVP (Phase 2)
• | Explorer band (Grades 4-5) — extend AFTER retention is proven
• | Audio / TTS instructions (gate word-problems behind this; G1 uses numeric+visual at launch)
• | Hindi / regional languages
• | Supporting character cast (just Tinku for launch)
• | Sound design pack (stock sounds acceptable at launch)
• | WhatsApp stickers, mom-influencer campaigns, paid ads
• | Sibling family-plan billing logic (single sub is fine to start)
• | Exam-season crash packs
• | A/B testing infrastructure
Far future (Phase 3-4)
• | iOS launch (~Month 6)
• | B2B school sales (your fastest-rupee lever — but needs case studies first)
• | State boards (Maharashtra/UP) — the big engine-leverage play, Year 2
• | Direct web billing via Razorpay (only past ~₹3-5L/month)
• | Second subject / Grades 6-8 Challenger band
Deliberately cut to ship faster (do NOT add these)
• | Multiplayer / social features
• | Video lessons (your visual+interactive modules replace these — don't build a video pipeline)
• | Custom backend (Firebase covers auth/db/analytics/hosting — no servers to run)
• | Gendered themes (kid-selectable skins later instead)
• | More than ~5 templates at launch (cover counting+add+subtract+place value; rest post-launch)

## Roadmap Gates
Roadmap Decision Gates (Plan A summary)
Full detail in roadmap-plan-a.md. Until Month 6: measure RETENTION & REVIEWS, not revenue.
Quarter | Focus | Target metrics | Decision gate
Pre-launch (now->mid-Jul) | Build MVP, start Families Policy review, recruit seed parents | App passes review; 3 kid-tests done; D7 measurable | Do kids return on day 2 without being forced? Yes->launch. No->delay 2 weeks, fix loop.
Q1 (Jul-Sep) | Launch, prove retention, chase reviews | 200-2000 installs; D7>=20%; 20+ reviews@4.3+; revenue ₹0-25k (₹0 OK) | D7>=20%? Yes->expand. 15-20%->fix first. <15%->STOP, Plan B.
Q2 (Oct-Dec) | Explorer band; post-Diwali school push; first paid-ads test | 3-10k installs; retention holding; 1-2 school deals; ₹15-60k/mo | Revenue growing MoM AND retention holding? Both yes->scale. Else fix monetization or pivot B2B (Plan C).
Q3 (Jan-Mar) | Audio+Hindi; iOS launch; referral mechanic | 10-30k installs; ₹40k-1.5L/mo; a profitable channel found | Revenue>=₹50k AND a profitable channel? Yes->Year2 scale. No but growing->lifestyle fork. Stalled->Plan B/C.
Q4 (Apr-Jun) | Consolidate; 2nd school buying window; tech debt | ₹50k-2L/mo; few thousand active kids; 5-20 school accounts | Choose Year 2 path: scale fork or lifestyle fork.
Year 2 | Second board (engine leverage!); Grades 6-8; B2B pillar; Indian entity | ₹2-10L/mo if Y1 retention strong | Scale fork (team, capital) vs lifestyle fork (solo, niche).
Year 3 | Scale OR specialize | Fundable/self-sustaining, or high-margin niche | Deliberate choice based on Y2 trajectory & appetite.